**Action Plan 2022-2023**

|  |  |  |  |
| --- | --- | --- | --- |
| Eco-Schools Topic  WATER | Action   1. Posters in toilets reminding staff and pupils to turn off taps. 2. Installation of water hippos and/or similar water saving devices. 3. Installation of water butts to water school plants during summer months. | Duration  Posters to be in place by Christmas  Fund raising for hippos and water butts to ensure they are in place by Easter. | Monitoring Method  Eco-monitors to check on taps in toilets at break and lunch on a rota. |
| Aim  Save water | Informing & Involving Plans  Assembly  Article in newsletter  Letter to PTFA | Final Evaluation  Compare this year’s water use with water use from 2021-2022 academic year. |
| Eco-Schools Topic  TRANSPORT | Action   1. Pupil led campaign   .   1. Implementation of school travel plan | Duration  Campaign for sustainable transport to be led by February half-term.  From then on, eco-committee to monitor. | Monitoring Method  Register of how many pupils use the walking bus each day.  Register of how many staff car share/use bikes/walk. |
| Aim  Increase pupils and staff who cycle or share  transport. | Informing & Involving Plans  Staff to share with governors  Letter for parents  Updates in newsletter | Final Evaluation |
| Eco-Schools Topic  WASTE | Action   1. Introduce collection of food waste 2. Sign up to Plastic Clever Schools and follow their programme to secure an award and ensure we are reducing plastic waste. | Duration  Initial trial in September. Food to then be collected twice weekly by Pedi-cargo.  Enroll in Plastic Clever in September – look to be a fully embedded part of school life by Easter – Stage 1 to have been completed by January. | Monitoring Method  Half termly updates from Pedi-cargo on how much plastic and food waste has been collected. |
| Aim  Reduce food waste  Reduce plastic waste | Informing & Involving Plans | Final Evaluation |